## Sheet1
See column descriptions in other tab
Story ID | User Story | Sprint Number | Story Priority | Story Status | Story Points
1 | As a user, I want to manually add food items to a list to match the items in my fridge. | 4 | H | IP | 2
2 | As a user, I want to remove items as they are consumed so that my inventory stays accurate. | 4 | H | IP | 2
3 | As a user, I want notifications when food is about to expire so that I can use it before it goes bad. | 5+ | M | B | 2
4 | As a user, I want to edit the quantity of an item as it is being used so that I know when I am running out. | 5 | M | B | 3
5 | As a user, I want to label items as “opened” so that I can track freshness of an item. | 5 | M | B | 3
6 | As a user, I want to see an estimate of how much money I have saved to keep me motivated to continue to use it. | 5 | L | B | 2
7 | As a user, I want to categorize items (produce, dairy, condiments, ect..) so I can be better organized. | 5 | L | B | 3
8 | As a user, I want a shopping list automatically generated from low-stock or expired items, so I can restock efficiently without forgetting anything. | 5+ | M | B | 5
9 | As a user, I want the tool to track leftover meals separately so I can prioritize eating them first. | 5+ | M | B | 3
10 | As a user, I want the app to suggest recipes based on the items currently in my fridge, so I can use what I already have and avoid buying extra ingredients. | 5+ | L | B | 5
11 | As a user, I want to be able to view all of the expiration dates on a calendar | 4 | M | IP | 2
12 | As a user, I want to be able to scan the barcodes of my groceries to add to the list of contents | 5+ | H | B | 5
13 | As a user, I want to be able to save frequently bought to items to a list | 5+ | H | B | 2
14 | As a user, I want to be able to add custom entries for certain items | 4 | H | IP | 2
15 | As a user, I want to be able to view what my roommates have purchased | 5+ | M | B | 5
16 | As a user, I want to be able to remove items with a single click | 5 | M | B | 2
17 | As a user, I want to be able to add multiple items from one trip | 5+ | M | B | 2
18 | As a user, I want to be able to view most commonly bought items | 5+ | L | B | 2
19 | As a user, I want filter fridge contents by name or category, so I can easily tell if I have certain items. | 5 | H | B | 3
20 | As a user, I want to sort fridge contents by time until expiry, so I can prevent items from getting old or stale. | 5 | H | B | 3
21 | As a user, I want to share my fridge contents with other people, so my roommates can see an accurate list as well. | 5+ | M | B | 5
22 | As a user, I want to set an alert for when items go below a specified quantity, so I know when I need to restock. | 5+ | M | B | 3
23 | As a user, I want to see when individual items were added to the fridge, so I know how old they are. | 5 | M | B | 2
Not User Stories
24 | Create functional requirements in SRS document | 1 | H | D | 2.5
25 | Create non-functional requirements in SRS document | 1 | H | D | 2.5
26 | Create Product Backlog | 1 | H | D | 1
27 | Create Sprint Backlog | 1 | H | D | 1
28 | Create README | 1 | H | D | 1
29 | Create UI Wireframes | 1 | H | D | 2
30 | Establish Build Environment | 1 | H | D | 1
31 | Create Use Case Descriptions | 2 | H | D | 2
32 | Create Use Case Diagrams | 2 | H | D | 2
33 | Create Architecture Design Document | 2 | M | D | 2
34 | Create Paper Prototype | 2 | H | D | 2
35 | Update Sprint Backlog | 2 | L | D | 1
36 | Begin UI Implementation | 2 | H | D | 3
37 | Continue UI implimentation | 3 | M | D | 5
38 | Automated testing | 3 | M | D | 6
39 | Continuous Intigration | 3 | M | D | 5
40 | Fix sprint review | 3 | L | D | 1
41 | Usability testing | 3 | M | D | 2
42 | Stimulous/resonse Sequences | 3 | L | D | 1
43 | Update sprint backlog | 3 | L | D | 2
44 | Update Product backlog | 3 | L | D | 2
45 | Upload documentation | 3 | M | D | 1.2
46 | Create video Walkthrough | 3 | M | D | 2
47 | Create domain model doc | 3 | M | D | 2
48 | UI Implementation | 4 | H | D | 8
49 | Revise Documentation | 4 | L | D | 3
50 | Review Documentation | 4 | M | D | 1
51 | Upload Documentation | 4 | M | D | 1
52 | Usability Testing | 4 | H | D | 2
53 | Create Detailed Technical Design | 4 | H | D | 4

## Description of Columns
ID: unique # for each story * Story: Contains the user stories (one story per row) in priority order ▪ Formatted as “As a <user role>, I need to <feature needed> because of <benefit>. o Sprint: The story’s sprint number (when it gets implemented) o Priority: H (high), M (medium), L (low) o Status: Backlog, To Do, IP (in progress), QC (quality checking), D (done) o Estimate / Story Points: Number of story points gives an indication of the difficulty of the story’s development and testing as well as possibly an estimate of the number of hours to design, implement, and test the story.
The basic idea of story points is a story with 3 points is 3x the effort as a 1 point story, 2 points is 2x the effort, etc. In general without much experience it's hard for you to estimate relative feature sizes. Just do your best. Here's more information https://www.mountaingoatsoftware.com/blog/what-are-story-points