## Sheet1
| See column descriptions in other tab | [8 empty] | Contribution %
Story ID | User Story | Task ID | Task | Sprint Number | Sprint Goal | Story Type | Story Points | Completion | Assignees | D | I | J | P | W
22 | Create Functional Requirements in SRS document | 22.1 | Create 4-6 Functional Requirements | 1 | Establish documentation, Development Environment, and UI design | KA | 0.5 | 100% | P |  |  |  | 100
|  | 22.2 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 22.3 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 22.4 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 22.5 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
23 | Create Non-Functional Requirements in SRS document | 23.1 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | P |  |  |  | 100
|  | 23.2 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 23.3 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 23.4 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 23.5 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
24 | Create Product Backlog | 24 | Create and Populate Product Backlog |  |  | KA | 1 | 100% | I |  | 100
25 | Create Sprint Backlog | 25 | Create and Populate Sprint Backlog |  |  | KA | 1 | 100% | I |  | 100
26 | Create README | 26 | Create README |  |  | KA | 1 | 100% | P
27 | Create UI Wireframes | 27 | Create 2-3 UI Wireframes |  |  | KA | 2 | 100% | J |  |  | 100
28 | Setup Build Environment | 28 | Setup Build Environment |  |  | T | 1 | 100% | D
29 | Create Use Case Descriptions | 29.1 | Create 5-10 Use Case Descriptions | 2 | Prototyping and Design, and Begin UI implementation | KA | 1 | 100% | W |  |  |  |  | 100
|  | 29.2 | Create 5-10 Use Case Descriptions |  |  | KA | 1 | 100% | J |  |  | 100
30 | Create Use Case Diagrams | 30.1 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | W |  |  |  |  | 100
|  | 30.2 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | P |  |  |  | 100
31 | Create Architecture Design document | 31.1 | Create UML Package Diagram |  |  | KA | 1 | 100% | J |  |  | 100
|  | 31.2 | Write Description and Justification |  |  | KA | 1 | 100% | D | 100
32 | Create Paper Prototype | 32 | Create Paper Prototype |  |  | KA | 2 | 100% | P |  |  |  | 100
33 | Update Sprint Backlog | 33 | Update Sprint Backlog for Deliverable 2 |  |  | KA | 1 | 100% | I |  | 100
34 | Begin UI Implementation | 34.1 | Create Homepage |  |  | T | 1 | 100% | J |  |  | 100
|  | 34.2 | Create login button |  |  | T | 1 | 100% | D | 100
|  | 34.3 | Create in depth view for pantry items |  |  | T | 1 | 100% | I |  | 100
35 | Continue UI implementation | 35.1 | Create application pages | 3 | Continue UI implementation | T | 1 | 100% | W |  |  |  |  | 100
|  | 35.2 | Create login and register pages |  |  | T | 2 | 100% | J |  |  | 100
|  | 35.3 | Update UI mockups |  |  | T | 2 | 100% | P |  |  |  | 100
36 | Automated testing | 36 | Create 2-3 Automated Tests for Login |  |  | KA | 3 | 100% | W |  |  |  |  | 100
37 | Setup Continuous Integration | 37 | Set up Continuous Integration |  |  | KA | 5 | 100% | J | 4 |  | 92 |  | 4
38 | Fix Sprint Review | 38 | Fix sprint review |  |  | P | 1 | 100% | D | 100
39 | Usability Testing | 39.1 | Update Usability Testing Script |  |  | KA | 1 | 100% | D | 100
|  | 39.2 | Conduct Usability Testing and write up results |  |  | KA | 1 | 100% | P |  |  |  | 100
40 | Create Stimulus/Response Sequences | 40 | Create Stimulus/response sequences in SRS |  |  | KA | 1 | 100% | W |  |  |  |  | 100
41 | Update Backlogs | 41.1 | Update Sprint Backlog for Deliverable 3 |  |  | P | 0.5 | 100% | D | 100
|  | 41.2 | Update Product Backlog for Deliverable 3 |  |  | P | 0.5 | 100% | I |  | 100
42 | Upload Documentation | 42.1 | Upload Sprint Backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 42.2 | Upload Product backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 42.3 | Upload Architecture Design and Domain Model |  |  | P | 0.2 | 100% | I |  | 100
|  | 42.4 | Upload Software Requirements Specification |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 42.5 | Upload Sprint Review |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 42.6 | Upload Use Case Diagram/Models and Descriptions |  |  | P | 0.2 | 100% | I |  | 100
43 | Create video walkthrough of progress | 43 | Create video walkthrough of progress |  |  | KA | 2 | 100% | W |  |  |  |  | 100
44 | Create Domain Model document | 44 | Create Domain Model document |  |  | P | 2 | 100% | I |  | 100
45 | UI Implementation | 45.1 | Login/Sign up functionality | 4 | Documentation and Progress on UI Functionality | T | 3 | 100% | D | 100
|  | 45.2 | Fix Continuous Integration |  |  | KA | 2 | 100% | J, D | 50 |  | 50
|  | 45.3 | Create video of implementation progress |  |  | KA | 2 | 100% | I, J, D, W | 25 | 25 | 25 | 25 | 25
|  | 45.4 | Create Firestore database to implement into FridgeFriend |  |  | T | 5 | 100% | D | 100
46 | Revise Documentation | 46.1 | Revisions on Software Requirements Specification |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 46.2 | Revisions on Use Case Diagrams/Descriptions |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 46.3 | Revisions on Architecture Design |  |  | P | 1 | 100% | W |  |  |  |  | 100
47 | Review Documentation | 47.1 | Review Architecture Design |  |  | P | 0.2 | 100% | P |  |  |  | 100
|  | 47.2 | Review Domain Model |  |  | P | 0.2 | 100% | I |  | 100
|  | 47.3 | Review Software Requirements Specification |  |  | P | 0.2 | 100% | D |  |  |  |  | 100
|  | 47.4 | Review Product and Sprint Backlogs |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 47.5 | Review Detailed Technical Design |  |  | P | 0.2 | 100% | W | 100
48 | Upload Documentation | 40.1 | Upload Domain Model and Detailed Technical Design |  |  | P | 0.2 | 100% | I |  | 100
|  | 40.2 | Upload Architecture Design and Use Case Diagrams |  |  | P | 0.2 | 100% | W | 100
|  | 40.3 | Upload SRS and Usability Testing documents |  |  | P | 0.2 | 100% | D |  |  |  |  | 100
|  | 40.4 | Upload Product and Sprint Backlog |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 40.5 | Upload Sprint Review |  |  | P | 0.2 | 100% | P |  |  |  | 100
49 | Usability Testing | 49 | Conduct Usability Testing and write up results |  |  | KA | 1 | 100% | P |  |  |  | 100
50 | Create Detailed Technical Design | 50.1 | Create Design "Class" Diagram |  |  | P | 2 | 100% | J |  |  | 100
|  | 50.2 | Create Design Patterns |  |  | P | 2 | 100% | J | 100
1 | As a user, I want a form to add food items to a list to match the items in my fridge. | 1.1 | Implement Item Inventory page |  |  | T | 1 | 100% | J |  |  | 100
|  | 1.2 | Create an Add Item form |  |  | T | 1 | 100% | J |  |  | 100
2 | As a user, I want to remove items as they are consumed so that my inventory stays accurate. | 2.1 | Implement Delete or Consumed button |  |  | T | 1 | 100% | J |  |  | 100
|  | 2.2 | Update database state to reflect real-time inventory |  |  | T | 1 | 100% | I |  | 100
11 | As a user, I want to be able to view all of the expiration dates on a calendar, so I can plan future meals using older items first. | 11.1 | Implement Expiration Calendar page |  |  | T | 1 | 100% | W |  |  |  |  | 100
|  | 11.2 | Implement Expiration Calendar CSS |  |  | T | 1 | 100% | W |  |  |  |  | 100
51 | UI Implementation | 51.1 | Login/Sign up functionality | 5 | Finish specific app features functionality and polish documentation | T | 6 | 100% | D | 100
|  | 51.2 | Add FridgeFriend logo to all pages |  |  | KA | 2 | 100% | P |  |  |  | 100
|  | 51.3 | Fix Continuous Integration |  |  | KA | 3 | 100% | D | 100
52 | Revise Documentation | 52.1 | Revisions on Domain Model |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 52.3 | Revisions on Software Requirements Specification |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 52.6 | Revisions on Detailed Technical Design |  |  | P | 2 | 100%
|  | 52.7 | Finalize Application logo |  |  | P | 1 | 100% | P |  |  |  | 100
53 | Review Documentation | 53.1 | Review documentation |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 53.2 | Review implementation |  |  | P | 0.2 | 100% | I |  | 100
|  | 53.3 | Review Test Plan document |  |  | P | 0.2 | 100% | P |  |  |  | 100
|  | 53.4 | Review Future Plans document |  |  | P | 0.2 | 100% | J |  |  | 100
54 | Upload Documentation | 54.1 | Upload Domain Model document |  |  | P | 0.2 | 100% | P |  |  | 100
|  | 54.2 | Upload Test Plan document |  |  | P | 0.2 | 100% | P |  |  |  | 100
|  | 54.3 | Upload Sprint Review 5 document |  |  | P | 0.2 | 100% | D | 100
|  | 54.4 | Upload Detailed Technical Design document |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 54.5 | Upload Use Case Diagrams/Models and Descriptions |  |  | P | 0.2 | 100% | D | 100
|  | 54.6 | Upload Software Requirements Specification |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 54.7 | Upload Product and Sprint Backlogs |  |  | P | 0.2 | 100% | I |  | 100
|  | 54.8 | Upload Architecture Design document |  |  | P | 0.2 | 100% | J |  |  |  | 100
|  | 54.9 | Upload Future Plans document |  |  | P | 0.2 | 100% | J |  |  | 100
55 | Create Test Plan document | 55 | Create Test Plan document |  |  | P | 3 | 100% | W |  |  |  |  | 100
56 | Create Future Plans document | 56 | Create Future Plans document |  |  | P | 1 | 100% | W |  |  |  |  | 100
57 | Update Backlogs | 57.1 | Update Sprint Backlog for Deliverable 5 |  |  | P | 0.5 | 100% | W |  |  |  |  | 100
|  | 57.2 | Update Product Backlog for Deliverable 5 |  |  | P | 0.5 | 100% | W |  |  |  |  | 100
58 | Final Presentation Video | 58 | Record Final Presentation Video |  |  | P | 2 | 100% | J, D, P, I, W | 20 | 20 | 20 | 20 | 20
1 | As a user, I want a form to add food items to a list to match the items in my fridge. | 1.1 | Implement add item functionality |  |  | T | 2 | 100% | J |  |  | 100
|  | 1.2 | Create foodItem collection in Firebase |  |  | T |  | 100% | J |  |  | 100
5 | As a user, I want to label items as “opened” so that I can track freshness of an item. | 5 | Add binary field to foodItem collection in Firebase |  |  | T |  | 100% | J |  |  | 100
7 | As a user, I want to categorize items (produce, dairy, condiments, etc.) so I can be better organized. | 7 | Add category in Firestore for item category |  |  | T | 2 | 100% | J |  |  | 100
17 | As a user, I want filter items by item location. | 17 | Add filter functionality to show a specific location |  |  | T | 2 | 100% | I |  | 100
18 | As a user, I want to sort fridge contents by time until expiry, so I can prevent items from getting old or stale. | 18 | Add sort functionality for users to sort items by expiration dates |  |  | T | 2 | 100% | I |  | 100

## Description of Columns
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users), P (Progress documentation). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.