## Sheet1
| See column descriptions in other tab | [8 empty] | Contribution %
Story ID | User Story | Task ID | Task | Sprint Number | Sprint Goal | Story Type | Story Points | Completion | Assignees | D | I | J | P | W
24 | Create 15-30 functional requirements in SRS document | 24.1 | Create 4-6 Functional Requirements | 1 | Establish documentation, Development Environment, and UI design | KA | 0.5 | 100% | P |  |  |  | 100
|  | 24.2 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 24.3 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 24.4 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 24.5 | Create 4-6 Functional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
25 | Create 10-15 non-functional requirements in SRS document | 25.1 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | P |  |  |  | 100
|  | 25.2 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 25.3 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 25.4 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 25.5 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
26 | Create Product Backlog | 26 | Create and Populate Product Backlog |  |  | KA | 1 | 100% | I |  | 100
27 | Create Sprint Backlog | 27 | Create and Populate Sprint Backlog |  |  | KA | 1 | 100% | I |  | 100
28 | Create README | 28 | Create Readme |  |  | KA | 1 | 100% | P
29 | Create UI Wireframes | 29 | Create 2-3 UI Wireframes |  |  | KA | 2 | 100% | J |  |  | 100
30 | Setup Build Environment | 30 | Setup Build Environment |  |  | T | 1 | 100% | D
31 | Create 10-20 Use Case Descriptions | 31.1 | Create 5-10 Use Case Descriptions | 2 | Prototyping and Design, and Begin UI implementation | KA | 1 | 100% | W |  |  |  |  | 100
|  | 31.2 | Create 5-10 Use Case Descriptions |  |  | KA | 1 | 100% | J |  |  | 100
32 | Create 2-4 Use Case Diagrams | 32.1 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | W |  |  |  |  | 100
|  | 32.2 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | P |  |  |  | 100
33 | Create Architecture Design Document | 33.1 | Create UML Package Diagram |  |  | KA | 1 | 100% | J |  |  | 100
|  | 33.2 | Write Description and Justification |  |  | KA | 1 | 100% | D | 100
34 | Create Paper Prototype | 34 | Create Paper Prototype |  |  | KA | 2 | 100% | P |  |  |  | 100
35 | Update Sprint Backlog | 35 | Update Sprint Backlog for Deliverable 2 |  |  | KA | 1 | 100% | I |  | 100
36 | Begin UI Implementation | 36.1 | Create Homepage |  |  | T | 1 | 100% | J |  |  | 100
|  | 36.2 | Create sign in button |  |  | T | 1 | 100% | D | 100
|  | 36.3 | Create in depth view for pantry items |  |  | T | 1 | 100% | I |  | 100
37 | Continue UI implementation | 37.1 | Create application pages | 3 | Continue UI implementation | T | 1 | 100% | W |  |  |  |  | 100
|  | 37.2 | Create sign in page |  |  | T | 2 | 100% | J |  |  | 100
|  | 37.3 | Update UI mockups |  |  | T | 2 | 100% | P |  |  |  | 100
38 | Automated testing | 38.1 | Auto Testing 1-3 |  |  | KA | 3 | 100% | W |  |  |  |  | 100
|  | 38.2 | Auto Testing login |  |  | KA | 3 | 100% | W |  |  |  |  | 100
39 | Continuous Integration | 39 | Continuous Integration |  |  | KA | 5 | 100% | J | 4 |  | 92 |  | 4
40 | Fix sprint review | 40 | Fix sprint review |  |  | P | 1 | 100% | D | 100
41 | Usability testing | 41.1 | Upload and fix |  |  | KA | 1 | 100% | D | 100
|  | 41.2 | Update |  |  | KA | 1 | 100% | P |  |  |  | 100
42 | Stimulus/response Sequences | 42 | Stimulus/response Sequences |  |  | KA | 1 | 100% | W |  |  |  |  | 100
43 | Update sprint backlog | 43 | Update sprint backlog |  |  | P | 2 | 100% | D | 100
44 | Update Product backlog | 44 | Update product backlog |  |  | P | 2 | 100% | I |  | 100
45 | Upload documentation | 45.1 | Sprint backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.2 | Product backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.3 | Architecture design and domain |  |  | P | 0.2 | 100% | I |  | 100
|  | 45.4 | SRS |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 45.5 | Sprint Review |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.6 | Use case diagram/models |  |  | P | 0.2 | 100% | I |  | 100
46 | Create video Walkthrough | 46 | Create video Walkthrough |  |  | KA | 2 | 100% | W |  |  |  |  | 100
47 | Create domain model doc | 47 | Create domain model doc |  |  | P | 2 | 100% | I |  | 100
48 | UI Implementation | 48.1 | Finish Login/Sign up functionality | 4 | Documentation and Progress on UI Functionality | T | 4 | 100% | D | 100
|  | 48.2 | Fix Continuous Integration |  |  | KA | 2 | 100% | J, D | 50 |  | 50
|  | 48.3 | Create video of implementation progress |  |  | KA | 2 | 100% | I, J, D, W | 25 | 25 | 25 | 25 | 25
49 | Revise Documentation | 49.1 | Revisions on Software Requirements Specification |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 49.2 | Revisions on Use Case Diagrams/Descriptions |  |  | P | 1 | 100% | P |  |  |  | 100
|  | 49.3 | Revisions on Architecture Design |  |  | P | 1 | 100% | W |  |  |  |  | 100
50 | Review Documentation | 50.1 | Architecture Design |  |  | P | 0.2 | 100% | P |  |  |  | 100
|  | 50.2 | Domain Model |  |  | P | 0.2 | 100% | I |  | 100
|  | 50.3 | Software Requirements Specification |  |  | P | 0.2 | 100% | D |  |  |  |  | 100
|  | 50.4 | Product and Sprint Backlogs |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 50.5 | Detailed Technical Design |  |  | P | 0.2 | 100% | W | 100
51 | Upload Documentation | 51.1 | Domain Model and Detailed Technical Design |  |  | P | 0.2 | 100% | I |  | 100
|  | 51.2 | Architecture Design and Use Case Diagrams |  |  | P | 0.2 | 100% | W | 100
|  | 51.3 | SRS and Usability Testing |  |  | P | 0.2 | 100% | D |  |  |  |  | 100
|  | 51.4 | Product and Sprint Backlogs |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 51.5 | Sprint Review |  |  | P | 0.2 | 100% | P |  |  |  | 100
52 | Usability Testing | 52.1 | Update Usability Testing Script |  |  | KA | 1 | 100% | P |  |  |  | 100
|  | 52.2 | Conduct Usability Testing |  |  | KA | 1 | 100% | P |  |  |  | 100
53 | Create Detailed Technical Design | 53.1 | Create Design "Class" Diagram |  |  | P | 2 | 100% | J |  |  | 100
|  | 53.2 | Create Design Patterns |  |  | P | 2 | 100% | J | 100
1 | As a user, I want to manually add food items to a list to match the items in my fridge. | 1.1 | Implement Item Inventory page |  |  | T | 1 | 100% | J |  |  | 100
|  | 1.2 | Create an Add Item form |  |  | T | 1 | 100% | J |  |  | 100
2 | As a user, I want to remove items as they are consumed so that my inventory stays accurate. | 2.1 | Implement Delete or Consumed button |  |  | T | 1 | 100% | J |  |  | 100
|  | 2.2 | Update database state to reflect real-time inventory |  |  | T | 1 | 100% | I |  | 100
11 | As a user, I want to be able to view all of the expiration dates on a calendar | 11.1 | Implement Expiration Calendar page |  |  | T | 1 | 100% | W |  |  |  |  | 100
|  | 11.3 | Implement Expiration Calendar CSS |  |  | T | 1 | 100% | W |  |  |  |  | 100

## Description of Columns
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users), P (Progress documentation). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.