## Sheet1
| See column descriptions in other tab | [8 empty] | Contribution %
Story ID | User Story | Task ID | Task | Sprint Number | Sprint Goal | Story Type | Story Points | Completion | Assignees | D | I | J | P | W
24 | Create 15-30 functional requirements in SRS document | 24.1 | Create 4-6 Fucntional Requirements | 1 | Establish documentation, Development Environment, and UI design | KA | 0.5 | 100% | P |  |  |  | 100
|  | 24.2 | Create 4-6 Fucntional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 24.3 | Create 4-6 Fucntional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 24.4 | Create 4-6 Fucntional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 24.5 | Create 4-6 Fucntional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
25 | Create 10-15 non-functional requirements in SRS document | 25.1 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | P |  |  |  | 100
|  | 25.2 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | W |  |  |  |  | 100
|  | 25.3 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | D | 100
|  | 25.4 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | I |  | 100
|  | 25.5 | Create 2-3 Non-Functional Requirements |  |  | KA | 0.5 | 100% | J |  |  | 100
26 | Create Product Backlog | 26 | Create and Polulate Product Backlog |  |  | KA | 1 | 100% | I |  | 100
27 | Create Sprint Backlog | 27 | Create and Populate Sprint Backlog |  |  | KA | 1 | 100% | I |  | 100
28 | Create README | 28 | Create Readme |  |  | KA | 1 | 100% | P
29 | Create UI Wireframes | 29 | Create 2-3 UI Wireframes |  |  | KA | 2 | 100% | J |  |  | 100
30 | Setup Build Environment | 30 | Setup Build Environment |  |  | T | 1 | 100% | D
31 | Create 10-20 Use Case Descriptions | 31.1 | Create 5-10 Use Case Descriptions | 2 | Prototyping and Design, and Begin UI implementation | KA | 1 | 100% | W |  |  |  |  | 100
|  | 31.2 | Create 5-10 Use Case Descriptions |  |  | KA | 1 | 100% | J |  |  | 100
32 | Create 2-4 Use Case Diagrams | 32.1 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | W |  |  |  |  | 100
|  | 32.2 | Create 1-2 Use Case Diagrams |  |  | KA | 1 | 100% | P |  |  |  | 100
33 | Create Architecture Design Document | 33.1 | Create UML Package Diagram |  |  | KA | 1 | 100% | J |  |  | 100
|  | 33.2 | Write Description and Justification |  |  | KA | 1 | 100% | D | 100
34 | Create Paper Prototype | 34 | Create Paper Prototype |  |  | KA | 2 | 100% | P |  |  |  | 100
35 | Update Sprint Backlog | 35 | Update Sprint Backlog for Deliverable 2 |  |  | KA | 1 | 100% | I |  | 100
36 | Begin UI Implementation | 36.1 | Create Homepage |  |  | T | 1 | 100% | J |  |  | 100
|  | 36.2 | Create sign in button |  |  | T | 1 | 100% | D | 100
|  | 36.3 | Create in depth view for pantry items |  |  | T | 1 | 100% | I |  | 100
37 | Continue UI implimentation | 37.1 | Create application pages | 3 | Continue UI implementation | T | 1 | 100% | W |  |  |  |  | 100
|  | 37.2 | Create sign in page |  |  | T | 2 | 100% | J |  |  | 100
|  | 37.3 | Update UI mock ups |  |  | T | 2 | 100% | P |  |  |  | 100
38 | Autimated testing | 38.1 | Auto Testing 1-3 |  |  | KA | 3 | 100% | W |  |  |  |  | 100
|  | 38.2 | Auto Testing login |  |  | KA | 3 | 100% | W |  |  |  |  | 100
39 | Continuous Intigration | 39 | Continuous Integration |  |  | KA | 5 | 100% | J | 4 |  | 92 |  | 4
40 | Fix sprint review | 40 | Fix sprint review |  |  | P | 1 | 100% | D | 100
41 | Usability testing | 41.1 | Upload and fix |  |  | KA | 1 | 100% | D | 100
|  | 41.2 | Update |  |  | KA | 1 | 100% | P |  |  |  | 100
42 | Stimulous/resonse Sequences | 42 | Stimulous/resonse Sequences |  |  | KA | 1 | 100% | W |  |  |  |  | 100
43 | Update sprint backlog | 43 | Update sprint backlog |  |  | P | 2 | 100% | D | 100
44 | Update Product backlog | 44 | Update product backlog |  |  | P | 2 | 100% | I |  | 100
45 | Upload documentation | 45.1 | Sprint backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.2 | Product backlog |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.3 | Architecture design and domain |  |  | P | 0.2 | 100% | I |  | 100
|  | 45.4 | SRS |  |  | P | 0.2 | 100% | J |  |  | 100
|  | 45.5 | Sprint Review |  |  | P | 0.2 | 100% | W |  |  |  |  | 100
|  | 45.6 | Use case diagram/models |  |  | P | 0.2 | 100% | I |  | 100
46 | Create video Walkthrough | 46 | Create video Walkthrough |  |  | KA | 2 | 100% | W |  |  |  |  | 100
47 | Create domain model doc | 47 | Create domain model doc |  |  | P | 2 | 100% | I |  | 100

## Description of Columns
o Sprint Goal and Number. o Story copied from the project backlog or a sprint task story. o Story Type: F (functional), NF (non-functional) with a subtype: B (bug), T (technical work), KA(knowledge acquisition, technical or design/users), P (Progress documentation). o Story Points. o Story Points Completed. o Team Member Names and percentage of contribution to the story.